Section Cover Page

Section 01000 1999-08-24 General Requirements

Use this Section to specify, in a single concise Section, the following:

.1	Essential administrative, procedural, temporary facilities and controls, and contract close-out requirements (i.e. all Division 1 requirements).

.2	Requirements which are not addressed or adequately addressed in the General Conditions.

.3	Any other non-technical requirements which are unique to the project.

This Section addresses, in article 7, "prime contractor" responsibility for work site safety, pursuant to the Occupational Health and Safety Act (Alberta).  See Data Sheet for additional information on this topic.  Note that if this Section, or article 7, are omitted, the Owner may retain "prime contractor" responsibility for the work site.

This Master Specification Section contains:

.1	This Cover Page

.2	Data Sheet - Editing

.3	Data Sheet - Prime Contractor Responsibility for Work Site Safety

.4	Specification Section Text:

.1	Work of This Contract

.2	Contract Time

.3	Contractor's Use of Premises

.3	Restrictions on Contractor's Use of Premises

.4	Unit Prices - Measurement for Payment by Owner

.4	Unit Prices - Measurement for Payment by Contractor

.5	Coordination

.6	Project Meetings

.7	Work Site Safety - This Contractor is "Prime Contractor"

.7	Work Site Safety - Other Contractor is "Prime Contractor"

.8	Submittals

.9	Quality Control

.10	Temporary Facilities and Controls

.11	Overloading and Cleaning of Streets

.12	Contract Close-out

The Specification Section text contains articles that are commonly necessary and appropriate for small projects, but must still be edited to suit the nature of the work.  Use the following list of possible additional article headings as a checklist to identify other requirements that may need to be specified in this Section.

.1	Related Work by Other Contractors

.2	Materials Supplied or Installed Under Separate Contracts

.3	Related Work by Owner

.4	Materials Supplied by Owner

.5	Preordered Materials

.6	Work Sequence

.7	Coordination

.9	Regulatory Requirements

.10	Special Project Procedures

.15	Start-Up

.16	Contract Acceptance

.17	Warranty

.18	Maintenance

Where appropriate, selected narrow-scope Division 1 - General Requirements Sections from the Health Facilities or Basic Master Specification may be used in lieu of, or in addition to, this Section, (e.g. HFMS Section 01212 - Allowances) provided they are edited extensively to avoid "overspecifying".

The Occupational Health and Safety Act effectively requires every construction "work site" to have a "prime contractor", a designation that carries with it certain legislated responsibilities.  Since a construction contractor is normally in the best position to fulfill these responsibilities, the "prime contractor" designation should, whenever possible, be delegated to a single construction contractor, by explicit agreement in the construction contract. If this is not done, the owner is, by default, the "prime contractor" and carries the attendant responsibilities.

For every contract, a determination must be made as to whether the contractor for the contract under consideration should be the "prime contractor" for the "work site" or whether some other contractor already has, or will be given, this designationee  The "work site" is the location (physical space) in which the contractor for the contract under consideration (or any of its subcontractors) is likely to have workers "engaged in any occupation".

For "single contract" projects, the single contractor should be "prime contractor".  For "multiple contract" projects, the contractor who will utilize the site to the greatest extent and occupy it for the longest time should be "prime contractor".

In this context a "single contract" could be:

-	where the Owner enters into only one contract for the entire project, or

-	where the Owner enters into more than one contract, but each contract is separated from all of the others by either time or space.  For example, a contract for carpet replacement and a separate contract for painting, both of which will be done in the same physical space but will follow one another in time, would be single contracts (separated by time). Similarly, a contract for tenant improvements on one floor of a building and another separate contract for tenant improvements on another floor of the same building, both of which will be done at the same time, would also be single contracts (separated by space).

A "multiple contract" project in this context is where two or more contractors contracting directly with the Owner will be performing work concurrently (at the same time) and at the same "work site" (same space).

END OF DATA SHEETS

1.	WORK OF THIS CONTRACT

SPEC NOTE:  Specify in very general and simple terms the nature of the work.

.1	Work of this Contract comprises the following:

.1	[                       ].

SPEC NOTE:  Include the following for demolition projects.

.2	Legal Description:  [                                   ].

.3	Municipal Address:  [                                   ].

SPEC NOTE:  Include the following for site development projects requiring work outside of property lines.

.4	Physical Limits:  Work of the Contract is not necessarily restricted to work within property lines of site, but includes all Work required by Contract Documents, both within and outside property lines.

2.	CONTRACT TIME

.1	Complete the Work within the time specified in Section [00413 - Stipulated Price Bid and Contract Form] [00428 - Unit Price Bid and Contract Form].

3.	CONTRACTOR'S USE OF PREMISES

SPEC NOTE:  Include this article if premises will be  unoccupied or if user occupancy will not affect the work in any way, and Contractor will have unhindered access to the site.

.1	Contractor shall have complete and exclusive use of premises for performance of the Work.  Contractor shall assume responsibility for premises assigned to him.

OR

3.	RESTRICTIONS ON CONTRACTOR'S USE OF PREMISES

SPEC NOTE:  Include this article if premises will be occupied and Contractor's use thereof will be restricted.

.1	Contractor's use of premises will be restricted due to user occupancy and use of the facility.

SPEC NOTE:  Specify in as much detail as necessary, all of the constraints and special requirements that will be imposed on the Contractor on account of the work being carried out in or adjacent to an occupied facility.  Consider issues such as work area limits, restricted use of facilities, restricted use of building services, work sequence, hours of work restrictions, disruption of building services restrictions, temporary construction, temporary facilities, noise control, security controls, signs, moving and protection of user's furnishings and equipment, etc.

.2	[                      ].

.3	[                      ].

.4	[                      ].

.5	Cooperate and coordinate Work with the Owner and facility users to minimize conflict and facilitate usage.

4.	UNIT PRICES - MEASUREMENT FOR PAYMENT BY OWNER

SPEC NOTE:  Include this article on unit price contracts where Owner will provide field engineering survey services.

.1	Quantities of Work will be measured and calculated by Owner and submitted to Contractor for verification.

.2	Contractor shall, within seven Days after date of receipt, notify Owner in writing of any disputed quantities, otherwise the quantities shall be considered verified by the Contractor.

OR

4.	UNIT PRICES - MEASUREMENT FOR PAYMENT BY CONTRACTOR

SPEC NOTE:  Include this article on unit price contracts where Contractor is to provide field engineering survey services.

.1	Within seven Days after date of commencement of the Contract, submit proposed method of calculating quantities, for Owner's approval.  Do not proceed with the Work prior to such approval.

.2	Quantities shall be measured, calculated and certified correct by an independent engineering survey firm.

.3	Submit quantity calculations to Owner for verification.

.4	The Owner reserves the right to retain and pay for an independent surveyor to verify quantities submitted by Contractor.

.5	Owner will inform Contractor of any disputed quantities.

5.	COORDINATION

.1	Where installation of one part of the Work is dependent on installation of other components, either before or after its own installation, schedule and coordinate construction activities in the sequence required to obtain the best results.

.2	Comply with manufacturer's installation instructions and recommendations, to the extent that those instructions and recommendations are more explicit or stringent than requirements contained in Contract Documents.

.3	Provide attachment and connection devices and methods necessary for securing Work.  Secure Work true to line and level.  Allow for expansion and building movement.

.4	Do the cutting and remedial work required to make the several parts of the Work come together properly.

6.	PROJECT MEETINGS

.1	Prior to start of any work, a pre-construction meeting shall be held by the Owner and the Contractor to examine and discuss the Work of the Contract.

.2	Schedule regular construction progress meetings, at the site, every two weeks for the duration of the contract, or as otherwise directed by Owner.

7.	WORK SITE SAFETY - THIS CONTRACTOR IS "PRIME CONTRACTOR"

SPEC NOTE:  Use this article to specify that this Contractor will have "prime contractor" responsibility for work site safety, pursuant to the Occupational Health and Safety Act.  Refer to Data Sheet for guidance information on this topic.

.1	The Contractor shall, for the purposes of the Occupational Health and Safety Act (Alberta), and for the duration of the Work of this Contract:

.1	be the "prime contractor" for the "work site", and

.2	do everything that is reasonably practicable to establish and maintain a system or process that will ensure compliance with the Act and its regulations, as required to ensure the health and safety of all persons at the "work site".

.2	The Contractor shall direct all subcontractors, sub-subcontractors, other contractors, employers, workers and any other persons at the "work site" on safety related matters, to the extent required to fulfill its "prime contractor" responsibilities pursuant to the Act, regardless of:

.1	whether or not any contractual relationship exists between the Contractor and any of these entities, and

.2	whether or not such entities have been specifically identified in this Contract.

SPEC NOTE:  Include following clause for single contract projects, as described in Data Sheet.

.3	The Owner does not anticipate that there will be any contractors, other than those performing the Work of this Contract, engaged in work at the "work site" during the performance of the Work of this Contract.

OR

SPEC NOTE:  Include following clause for multiple contract projects, as described in Data Sheet.

.3	The Owner anticipates that other contractors will be engaged in work at the "work site" concurrently with the Work of this Contract.  These may include, but are not necessarily limited to, contractors performing work under the following other contracts:

SPEC NOTE:  Provide a comprehensive listing of all known or anticipated other contracts, and if known, names of contractors, for all work that may be performed at the "work site" concurrently with the work of this contract.  This could include property management services contractors, if applicable.

.1	[                         ]. [The contractor for this other contract is [                      ]].

.2	[                         ]. [The contractor for this other contract is [                      ]].

.3	[                         ]. [The contractor for this other contract is [                      ]].

OR

7.	WORK SITE SAFETY - OTHER CONTRACTOR IS "PRIME CONTRACTOR"

SPEC NOTE:  Use this article to specify that a contractor other than this Contractor will have "prime contractor" responsibility for work site safety, pursuant to the Occupational Health and Safety Act.  Refer to Data Sheet for guidance information on this topic.

.1	For the purposes of the Occupational Health and Safety Act (Alberta), the "prime contractor" for the "work site" will be the contractor for the following other contract, which will be performed concurrently with the Work of this Contract:

SPEC NOTE:  Identify other contract by name and, if known, insert name of designated "prime contractor".

.1	[                         ]. [The contractor for this other contract is [                      ]].

SPEC NOTE:  Ensure that the above named "prime contractor's" contract will extend for the duration of this Contract.  If it will not, modify this article as required to designate who will be the "prime contractor" in the absence of the above named "prime contractor".  (It should be either this Contractor or some other contractor.)

.2	Comply with the Act and its regulations, as required to ensure the health and safety of all persons at the "work site".

.3	Cooperate with, and comply promptly with any directives of, the above designated "prime contractor" on safety related matters.

8.	SUBMITTALS

.1	W.C.B. Submittals:  Submit certificate of an account with Workers Compensation Board prior to commencement of Work.  Submit letter of clearance with application for payment of holdback, if applicable, and with application for final payment.

SPEC NOTE:  W.C.B. submittals need not be specified for contracts under $10,000 in value.

.2	Work Schedule:  Prior to start of work, submit a schedule indicating scheduled start and completion dates for each construction activity.

.3	Shop Drawings and Product Data:  Submit [five] [       ] copies of shop drawings and product data required by the Contract Documents and for such other items as the Owner may reasonably request.  Do not proceed with work until related submission has been reviewed.

.4	Samples:  Submit duplicate samples required by the Contract Documents and for such other items as the Owner may reasonably request.

9.	QUALITY CONTROL

.1	Owner may employ services of independent testing agencies to establish if work complies with Contract Documents.  Owner will appoint and pay for services of such testing agency.

.2	Where tests or inspections, by Owner appointed testing agency, indicate work is not in accordance with the Contract Documents, additional tests or inspections, as Owner may require, to verify acceptability of corrected work, shall be paid for by Contractor.

10.	TEMPORARY FACILITIES AND CONTROLS

SPEC NOTE:  Specify any temporary facilities or temporary controls that must be provided by Contractor.  Specify temporary services (e.g. water, heat, power, telephone) and facilities (e.g. washrooms, elevators, loading docks, parking) that will be made available for use by the Contractor.  Specify any conditions applicable to such use by the Contractor.

.1	[                                   ]

.2	[                                   ]

.3	[                                   ]

.4	[                                   ]

11.	OVERLOADING AND CLEANING OF STREETS

SPEC NOTE:  Include this article only for projects involving earthwork.

.1	Vehicles employed for cartage of fill material shall not be loaded beyond rated limits, nor in such manner as to cause spillage.

.2	Clean up immediately spillage or tire tracking occurring upon public or private property.

12.	CONTRACT CLOSE-OUT

.1	Record Drawings:  Submit project record drawings indicating deviations from Contract Documents resulting from changed site conditions and changes ordered by Owner.

.2	Operation and Maintenance Data:  Submit [three] [       ] copies of operation and maintenance data required by the Contract Documents and for such other items as the Owner may reasonably request.

.3	Maintenance Materials: Leave maintenance materials required by the Contract Documents where directed by Owner.  Clearly label all items.

END OF SECTION