Section Cover Page

Section 00631 1999-07-01 Facility Start-Up Payments

Use this Section only when facility start-up procedures are specified (Section 01811).  This Section specifies amounts (ie. portions of the Contract Price) which are payable only upon achievement of certain milestones during Facility Start-Up.  These amounts place an arbitrary value on Facility Start-Up work; they do not constitute holdback, retention, security, nor cash allowances and should not be confused therewith.

This Master Specification Section contains:

.1	This Cover Sheet

.2	Specification Section Text:

.1	Related Sections

.2	Facility Start-Up Costs

.3	Facility Start-Up Amounts

.4	Facility Start-Up Payments

.5	Partial Payment for Facility Start-Up

1.	RELATED SECTIONS

.1	Payment Conditions:	Section 00630.

.2	Construction Schedules:	Section 01321.

OR

.2	Network Analysis Schedule:	Section 01322.

.3	Contract Price Breakdown:	Section 01330.

.4	Contractor Start-Up Report Forms:	Section 01335.

.5	Contract Acceptance Procedures:	Section 01775.

.6	Facility Start-Up Procedures:	Section 01811.

2.	FACILITY START-UP COSTS

.1	Facility Start-Up costs means all Contractor costs, including Subcontractor and Sub-subcontractor costs for performing Facility Start-Up work and providing related services as specified in Section 01811.

.2	Include Facility Start-Up costs in Contract Price.

3.	FACILITY START-UP AMOUNTS

.1	Notwithstanding payment conditions specified in Section 00630, and regardless of actual Facility Start-Up costs, portions of the Contract Price, in the following amounts, shall not become due and payable except as specified in Article 4.:

.1	Mechanical subcontract portion:	[$            ]

.2	Electrical subcontract portion:	[$            ]

.3	Prime Contract portion:	[$            ]

Total:	[$            ]

.2	Incorporate amounts specified above as separate line items in Contract Price breakdown specified in Section 01330.

4.	FACILITY START-UP PAYMENTS

.1	Facility Start-Up payments will be made upon completion of each sub-phase of Facility Start-Up as follows:

.1	Preparation for Facility Start-Up:  5% of total amount specified in 3.1 will be payable by Minister to Contractor provided that Minister has approved Facility Start-Up subschedules specified in Section [01321] [01322] and Contractor Start-Up report forms specified in Section 01335.

.2	Contractor Start-Up:  25% of total amount specified in 3.1 will be payable by Minister to Contractor provided that Minister has issued a Letter of Interim Acceptance.

.3	Performance Testing:  50% of total amount specified in 3.1 will be payable by Minister to Contractor provided that Minister has issued a Letter of Practical Completion.

.4	Fine Tuning:  20% of total amount specified in 3.1 will be payable by Minister to Contractor provided that Minister has issued a Letter of Final Acceptance.

.2	Payments specified in 4.1 shall not be subject to adjustment, regardless of actual Facility Start-Up costs.

.3	Facility Start-Up payments are separate from progress payments and payment of holdback specified in Section 00630.

.4	Facility Start-Up payments are not subject to holdback.

5.	PARTIAL PAYMENT FOR FACILITY START-UP

.1	When partial utilization of the Work by Minister is required and partial payment for Facility Start-Up is a condition of such partial utilization, the applicable conditions specified in this Section shall apply to the part of the Work to be utilized.

END OF SECTION